## Requirements
Carease Health — Warehouse WMS · Version 3 Requirements Built
Each requirement maps to a visible in-app badge (hover the amber 'V3' pill for its description). Status as of 2026-06-24.
Req ID | Category | Requirement (supervisor spec) | Where to find it in the app | In-app badge | Status | How it was verified | Notes
INV-1 | Inventory / Groups | Group building must be fast — no delay when adding a second/third item to a group. | Inventory ▸ Add Item ▸ Group ▸ 'Add items to this group' search | V3 · INV-1 | Met | Lightweight catalog picker + memoized lookups (code review). Data layer is O(1) per lookup. | Final confirmation is a quick in-browser click test in npm run dev.
SO-GRP-1 | Sales Order / Groups | A group is ONE line with a dropdown; changing its qty scales every item inside (5 groups → singles ×5, a double ×10). | Sales Order ▸ New/Edit SO ▸ Items (click ▾ on a group line) | V3 · SO-GRP-1 | Met | Automated: order 5 groups → tab/mount/MDM = 5, basket = 10; shipping draws each member scaled.
PO-1 | Purchase Order | Deposit auto-populates from each vendor's rule and stays editable. | Purchase Order ▸ New PO ▸ Deposit field | V3 · PO-1 | Met | Automated: deposit for a 30% vendor on $1,000 = $300; field stays editable after auto-fill.
PO-2 | Purchase Order | Clicking Save on a PO closes it. | Purchase Order ▸ open a PO ▸ Save | V3 · PO-2 | Met | Code: Save handler closes the PO dialog.
PO-3 | Purchase Order | After receiving, show the remaining payment owed. | Purchase Order ▸ open a PO ▸ Payments; green banner after Receive | V3 · PO-3 | Met | Automated: remaining = $600 after a $400 payment and stays correct after receiving.
PO-4 | Purchase Order | Payments are editable, flag when changed, and show a total. | Purchase Order ▸ open a PO ▸ Payments to vendor | V3 · PO-4 | Met | Automated: editing a payment sets the 'changed' flag; payments total = $600.
SO-1 | Sales Order | One search bar finds any recipient — facility, regional, employee, or provider. | Sales Order ▸ New SO ▸ 'Who is this SO for?' | V3 · SO-1 | Met | Automated: the recipient list contains all four recipient types.
SO-2 | Sales Order | Address line works like a Google address lookup (autocomplete). | Sales Order ▸ New SO ▸ Shipping info ▸ 'A new address (lookup)' | V3 · SO-2 (demo) | Met | Live OpenStreetMap autocomplete + offline local-suggestion fallback; hardened component. | Production uses Google Maps Places (noted in-app and in README).
SO-3 | Sales Order | Landed-cost math must add up (PO and SO with same items should reconcile). | Sales Order totals; Purchase Order landed cost | V3 · SO-3 | Met | Automated: SO goods ($1,050) = PO goods + landed ($1,050) for the same items. | SO total may exceed PO only by legitimate outbound freight.
SO-4 | Sales Order | Open any SO to edit & upload attachments (BOL / proof of delivery); show them under the Facility too. | Sales Order ▸ Open ▸ Attachments; Dashboard ▸ Facilities ▸ Manage | V3 · SO-4 | Met | Automated: a BOL uploaded on an SO appears in the facility's shipment documents (BOL + POD).
SO-5 | Sales Order | Shipping slips print one order per page; multiples to the same place numbered 1 of N, 2 of N. | Sales Order ▸ Shipping slips ▸ Print | V3 · SO-5 | Met | Code: slips grouped per address with 'x of n'; print CSS forces one slip per page.

## Verification
Verification Summary — automated checks + build
All checks pass as of 2026-06-24. Re-run anytime from the project folder.
Check suite | # Checks | Result | What it proves
_qa/test.mjs (3 user journeys + edge probes) | 51 | PASS | PO receiving/FIFO/multi-vendor Vendor bills; SO ship/short-stock back-order/employee asset assignment/reverse; cart assemble→assign→return make-whole→cart receipt.
_qa/req_check.mjs (V3 requirements) | 19 | PASS | Group qty scaling, deposit auto-fill, remaining-after-receiving, editable payments + total, PO/SO landed reconciliation, all-types recipient search, facility document visibility.
Production build (vite build) | — | PASS | 52 modules transformed and all page bundles rendered cleanly with the new requirement badges.

## Fixes & Enhancements
Fixes & Enhancements delivered in this round
Item | Type | Detail | Status
Shipment reversal double-count | Bug fix | Reversing a laptop/trivia shipment now also removes the employee asset assignment it created (previously the unit was counted in inventory AND as assigned). | Fixed + test
Live address autocomplete | Enhancement | Hardened: stale-response guard, response checks, offline local-suggestion fallback, clear loading/empty states, and a 'Google Maps in production' note. | Done
Stale production build | Maintenance | Rebuilt the production bundle so dist/ matches the latest source. | Done
V3 requirement badges | Enhancement | Added 12 in-app amber 'V3' badges with hover tooltips marking each requirement area for supervisor review. | Done