## Change Register
Carease WMS — Version 4 Change Register (all phases delivered)
Status 2026-06-24: every V4 item delivered & verified. 30/30 strict supervisor checks pass (v4_supervisor.mjs).
ID | Area | Supervisor ref | Requirement | Status | How it was verified
IT-1 | Item Types | Item Types | Three item kinds at add time: Single, Group, Assembly. | Delivered ✓
IT-2 | Item Types | Item Types | A Single can be flagged a tracked asset (laptop, gameshow, tablet; not cable). | Delivered ✓
IT-3 | Item Types | Item Types | Asset Single becomes a tracked asset when shipped out solo (not at receive). | Delivered ✓
IT-4 | Item Types | Item Types | A tablet inside an assembled cart is not its own asset. | Delivered ✓
IT-5 | Item Types | Item Types | Parts aren't assets; assembling removes parts + creates one asset. | Delivered ✓
AS-1 | Assemblies | Assemblies #1 | Cart types EDAN/VS8/Accutor, addable/changeable. | Delivered ✓
AS-2 | Assemblies | Assemblies #2 | Build screen shows group items too (groups + singles). | Delivered ✓
AS-3 | Assemblies | Assemblies #3 | Auto-fill asset fields from the group composition. | Delivered ✓
AS-4 | Assemblies | Assemblies #4 | Cart Code mandatory; carries all asset info. | Delivered ✓
AS-5 | Assemblies | Assemblies #5 | Facility/Regional fill at ship-out, not at build. | Delivered ✓
AS-6 | Assemblies | Assemblies #6 | Edit an assembly after it's built. | Delivered ✓
AS-7 | Assemblies | Assemblies #7 | Landed cost carries into the assembly. | Delivered ✓
PO-1 | Purchase Orders | PO #1 | Group on a PO is one scaling line (like SO). | Delivered ✓
PO-2 | Purchase Orders | PO #2 | Hide Record Deposit after a deposit is recorded. | Delivered ✓
PO-3 | Purchase Orders | PO #3 | Deposit % calculates off the bill total. | Delivered ✓
PO-4 | Purchase Orders | PO #4 | Manage Vendors (edit terms). | Delivered ✓
PO-5 | Purchase Orders | PO #5 | No new payment when fully paid. | Delivered ✓
INV-1 | Inventory | Inventory #1 | Pin the top header row on scroll. | Delivered ✓
SO-1 | Sales Orders | SO #1 | Ship a specific asset/assembly unit from an SO. | Delivered ✓
SO-2 | Sales Orders | SO (drop) | Remove multi-vendor-on-one-PO; build an SO mixing items/assemblies from different vendor origins. | Delivered ✓

## Decisions resolved
Open Decisions — resolved & implemented
ID | Decision | How it was resolved (implemented default)
D1 | Asset auto-fill mapping | Asset-field defaults live on each assembly definition (asset_defaults) and pre-fill the unit at build; user can override.
D2 | Asset field set | Cart Code (required), Cart Type, Key Type, BP Device, Cart Color, Tablet Number, captured components + FIFO cost; Facility/Regional at ship.
D3 | Asset creation timing | Assets are created at assembly (carts) and at ship-out (asset singles); never at PO receive.
D4 | Assembly-type management | Managed list seeded EDAN/VS8/Accutor with a Manage cart types screen to add/rename.
D5 | SO unit-selection UX | When an assembly/asset line ships, the available built units/assets are listed to pick from.

## Phasing
Phased Plan — status
All phases delivered & verified 2026-06-24.
Phase | Status | Scope | Acceptance
P0 | Delivered ✓ | INV-1, PO-1..5, SO-2 | Quick wins & removals shipped; harness re-baselined.
P1 | Delivered ✓ | IT-1, IT-2 | Item Types foundation (Single/Group/Assembly + asset flag).
P2 | Delivered ✓ | AS-1..4, AS-6, AS-7, IT-4, IT-5 | Assemblies: build with auto-fill, mandatory code, parts removed, one asset, editable, landed attached.
P3 | Delivered ✓ | IT-3, AS-5 | Assets mint at ship-out; facility/regional set at ship.
P4 | Delivered ✓ | SO-1 | SO ships a specific built unit/asset.
P5 | Delivered ✓ | Verify & docs | Harnesses green (test 54, req 19, v4 9, v4b 23, sup 29, v4_supervisor 30); clean build; docs updated.