## Amendment Register
# | Area | Supervisor requirement (amendment) | Status | How it was implemented | Verified by
IT-1 | Item Types | Three item types when adding an item: Single, Group, Assembly. | Built | Add dialog offers Single / Group / Assembly; catalog distinguishes all three. | supervisor_amendment.mjs [IT-1]
IT-2 | Item Types | A Single is not an asset; only assemblies are assets. | Built | itemIsAsset() always false; assets exist only as assembled units. | amendment_check, v4_supervisor [IT-2]
IT-3 | Item Types | Laptops & Gameshows are assembly-only (no longer standalone assets). | Built | Raw items flagged assembly_only; seeded single-item assemblies asm-laptop/-gameshow. | supervisor_amendment.mjs [AR]
AR-1 | Asset rule | Remove the 'enter asset info on receiving' prompt; items move into inventory. | Built | Receive commits straight to stock; asset-entry modal removed from PO page. | supervisor_amendment.mjs [AR-b]
AR-2 | Asset rule | Assembly-only item cannot be shipped on its own (must be assembled first). | Built | catalogShip excludes assembly_only items; only built units are shippable. | supervisor_amendment.mjs [AR-c, AR-d]
AR-3 | Asset rule | A flag when creating an item: 'can only be shipped as an assembly'. | Built | Add-item screen checkbox itemForm.assembly_only. | supervisor_amendment.mjs [AR-d]
AR-4 | Asset rule | Tablets inside a cart stay part of the cart's asset record (not own asset). | Built | Parts consumed into the cart unit; no separate asset minted. | supervisor_amendment.mjs [AR-e]
IV-1 | Inventory vs assembled | Parts in inventory are not assets; assemble 10 of 20 → 10 carts + 10 parts left. | Built | buildAssembly consumes via FIFO; remaining parts stay in stock. | supervisor_amendment.mjs [IV-a]
IV-2 | Inventory vs assembled | Parts uncommitted until assembled; can go toward any cart type. | Built | Shared part pools; no pre-commitment by cart type. | supervisor_amendment.mjs [IV-b]
IV-3 | Inventory vs assembled | Marking assembled removes parts and creates one asset with fields filled. | Built | One unit per build; code mandatory; fields captured. | supervisor_amendment.mjs [IV-c]
AS-1 | Assemblies | Cart types EDAN/VS8/Accutor; ability to add & change cart types. | Built | assemblyTypes list + addAssemblyType/updateAssemblyType; Manage cart types UI. | supervisor_amendment.mjs [AS-1]
AS-2 | Assemblies | Two kinds: cart (groups+singles) vs single-item (info only, no build). | Built | assembly_kind cart¦single; single-item build path with info fields. | supervisor_amendment.mjs [AS-2]
AS-3 | Assemblies | Auto-fill asset fields from the group composition. | Built | assemblyAutoFill: VS8 → CTA Cart / CTA Key / VS8. | supervisor_amendment.mjs [AS-3]
AS-4 | Assemblies | Cart Code mandatory; unit carries all cart/asset info. | Built | buildAssembly rejects blank code; unit stores fields. | supervisor_amendment.mjs [AS-4]
AS-5 | Assemblies | Assignment auto-fills at ship-out: carts→facility+Regional; laptops/gameshows→employee. | Built | shipSO assigns by assembly_kind. | supervisor_amendment.mjs [AS-5]
AS-6 | Assemblies | Edit an assembly after it is built. | Built | editAssemblyUnit; Edit on built unit. | supervisor_amendment.mjs [AS-6]
AS-7 | Assemblies | Landed cost carries into the assembly. | Built | FIFO unit cost (base+landed) captured into unit cost. | supervisor_amendment.mjs [AS-7]
PO-1 | Purchase Orders | Group on a PO is one line whose qty scales every part (like SO). | Built | kind:'group' single line; poLineGoods scales by per_group. | supervisor_amendment.mjs [PO-1]
PO-2 | Purchase Orders | Hide 'Record Deposit' after a deposit is recorded. | Built | Deposit block hidden once a Deposit payment exists. | supervisor_amendment.mjs [PO-2]
PO-3 | Purchase Orders | Deposit % calculates off the bill total (100% of $350 = $350). | Built | poDepositFor = total × pct / 100. | supervisor_amendment.mjs [PO-3]
PO-4 | Purchase Orders | Manage Vendors area to change existing vendor terms. | Built | Manage Vendors modal + updateVendor. | supervisor_amendment.mjs [PO-4]
PO-5 | Purchase Orders | No new payment option when fully paid. | Built | Record Payment hidden when poRemaining ≤ 0. | supervisor_amendment.mjs [PO-5]
INV-1 | Inventory | Pin the top header row of the items list. | Built | Sticky table header (sticky top-0). | supervisor_amendment.mjs [INV-1]
SO-1 | Sales Orders | Ship an assembly from an SO; pick the available built unit; assembly-only not loose. | Built | Assembly lines pick units via availableUnits; loose excluded. | supervisor_amendment.mjs [SO-1]
SO-2 | Sales Orders | Drop multi-vendor PO; build one SO mixing groups/assemblies from different vendors. | Built | Multi-vendor PO removed; SO mixes group + assembly lines. | supervisor_amendment.mjs [SO-2]
AR-1 | Assets | Bring the full company asset register into the app (8 classes) from the Cart List. | Built | 2,293 units seeded; tab per class with real columns. | asset_registry.mjs [SEED]
AR-2 | Assets | Correct the cart record (Cart Type = wheel; BP Machine = edan/vs8/accutar). | Built | Seed normalisation + display columns. | asset_registry.mjs [CART]
AR-3 | Assets | Holder is an Employee or a Facility only. | Built | Normalised on import; editor enforces it. | asset_registry.mjs [HOLD]
AR-4 | Assets | Add & edit any asset (code, status, holder, class fields). | Built | addAsset / updateAsset / nextAssetCode + edit modal. | asset_registry.mjs [WM]
AR-5 | Assets | Pagination — default 10, options 20/30/40/50. | Built | pageSize + Prev/Next + range. | asset_registry.mjs [WM]
AR-6 | Assets | Export the current view to CSV. | Built | exportCsv(). | asset_registry.mjs [WM]
AR-7 | Assets | Terminated employee → recover & return their assets. | Built | Returns — Terminated tab + recoverTerminatedAssets/returnAsset. | asset_registry.mjs / map_check
MAP-1 | Equipment Maps | New page: facilities on an OpenStreetMap of the US. | Built | Leaflet + facility rollup getters. | map_check.mjs [MAP]
MAP-2 | Equipment Maps | Markers; hover shows facility + equipment + team. | Built | divIcon pins + bindTooltip. | map_check.mjs [MAP/DETAIL]
MAP-3 | Equipment Maps | Click a facility → detail column (equipment, employees, their gear). | Built | selectedFacility + 3-column layout. | map_check.mjs [DETAIL]
MAP-4 | Equipment Maps | Facility & User search with autosuggest + dropdown; State & Regional filters. | Built | facSuggestions / userSuggestions + selects. | map_check.mjs [FAC/USR]
MAP-5 | Equipment Maps | Tick-box multi-select of facilities to view together. | Built | selectedIds + listSearch. | map_check.mjs [MULTI]
MAP-6 | Equipment Maps | First-name display; >=2 team members per facility (demo where sparse). | Built | shortName + facilityStaff. | map_check.mjs [NAME/DEMO]
MAP-7 | Equipment Maps | Notes: Google Maps API in production; real employees per facility in production. | Built | Banner + panel notes. | map_check.mjs [NOTE]
UI-1 | App-wide | Demo / production toggle for the NEW labels and notes. | Built | Change-notes switch + ReqTag gating. | build verified